## Slide 1: Round-table: Azure DevTest Labs
February 5, 2016, MLIT TnM

## Slide 2: TnM Projects: Teething problems prevail?
Project OLYC (part of STCY)
On-site vendor team in Copenhagen, DK with 5 persons, one additional resource in Madrid, ES without access to Maersk net
Dev PCs requested primo October 2015, delivered medio November 2015
Software provisioning of dev PCs via DevOps failed – workarounds used, work completed medio December 2015
Server environments ordered ultimo August 2015, delivered primo November, provisioning not complete to date.
Project only expected to run for 6 months
Project Market Plan 2.0
Off-shore vendor team in Mumbai and Delhi, IN with 20+ persons, approximately 1/3 of the team without access to Maersk net
Dev PCs requested primo June 2015 – delivered ultimo August 2015
Software provisioning of dev PCs via SD failed – workarounds used, work completed ultimo September 2015
Server environments ordered medio July 2015 – last environment delivered and provisioned primo November 2015

## Slide 3
No holistic dev PC provisioning process
No standard way to connect vendors to Maersk net
Unacceptably long lead times
Impossible to adjust PC park on the fly
Need to forecast server capacity upfront minimum 2 months before actual delivery
Impossible to adjust server capacity once delivered
Challenges:
Up to 90% idle time of dev server infrastructure
Impossible to re-use servers for different purposes/environments once set up

## Slide 4
TnM Projects: Wanna-be world
Self-service dev PC and server provisioning utilized by projects on emerging basis
Non-obtrusive, bureaucracy-free, on-demand service
Flexibility of capacity: add, remove, extend, reduce when/if needed in real-time
Project controlled capacity based on the allocated budget
No need to forecast capacity and types of servers ordered
Easy to bring geographically spread teams together via virtual networks

## Slide 5
TnM Projects: In the cloud
Powered by Azure DevTest Labs
Self-service portal utilizing the unlimited capacity of Azure
Allows to spin up the required number of VMs (dev PCs or servers) in real-time
Provides the required flexibility of infrastructure – in particular seen in the perspective of hard-to-predict emerging capacity needs in projects
Enables transferring of un-used capacity, e.g. a set of VMs covering one environment that is currently not in use can be used for another environment
Provides control to the up-time of the VMs and hence the implicated cost while eliminating idle time

## Slide 6
TnM Projects: In the cloud - Continued
Powered by Azure DevTest Labs
Project Manager can, e.g. be granted ownership of a single Lab and in this way control and manage the usage of VMs through the allocated budget
A list of enterprise approved software artefacts can be maintained in a centralized repository with project-level access control for self-service real-time provisioning
Standard Maersk PCs can be provided to developers, e.g. off‑shore vendors, to then let them self-configure development VMs in the allowed configuration and in the quantities needed
Azure virtual networks can be used to bring geographically distributed teams together during development
The overall enterprise capacity (the sum of all Labs) can be monitored and assessed, e.g. by a unit in MGIS for the sake of forecasting, reporting, budgeting and providing feedback to MLIT.